## Project
Total Project Tracking
Information in the columns A-E are filled in the project initiation; columns F-J to be filled by the end of each development iteration
# | Screen/Function | Feature | Actor | Screen/Function Description | In Charge | Status | Actual | Updated | Update Details
1 | HomePage | Landing | Admin, User, Guest | Displays an overview of the platform, including featured pickleball courts, sports products, and user options. | Trần Minh Trung | Done | iter1 | none
2 | User Login | Auth | Admin, User | This is a pop-up screen which allows the user to enter email & password to login; on this page, there are also links for user to register new information or reset the password for the case s/he forget it | Trần Minh Trung | Done | iter1 | none
3 | Register | Auth | User,Guest | Enables new users to create an account on the platform. | Trần Minh Trung | Done | iter1 | none
4 | Register with Google | Auth | User,Guest | Allows users to sign up quickly using their Google account. | Trần Minh Trung | Done | iter1 | none
5 | User Login with Google | Auth | User,Guest | Enables users to log in using their Google credentials. | Trần Minh Trung | Done | iter1 | none
6 | Forget Password | Auth | User,Guest | Provides an option to recover a forgotten password via email verification. | Trần Minh Trung | Done | iter2 | none
7 | Chagne Password | Auth | User | Allows users to update their password for security purposes. | Trần Minh Trung | Done | iter2 | none
8 | Search Field | Field | User, Admin, Guest | Users can search for available pickleball courts based on location, time, and availability. | Trần Minh Trung | Done | iter2 | none
9 | Search Product | Product | User, Admin, Guest | Enables users to search for sports products related to pickleball. | Phạm Lê Tấn Huy | Done | iter1 | none
10 | View Profile | Auth | User | Allows users to view their personal information, booking history, and order history. | Trần Minh Trung | Done | iter3 | none
11 | Edit Profile | Auth | User | Users can update their personal details, contact information, and preferences. | Trần Minh Trung | Done | iter3 | none
12 | Book Field Pickleball | Field | User | Users can reserve a pickleball court for a specific date and time. | Trần Minh Trung | To Do | iter3 | none
13 | Buy Product Sport | Product | User | Users can purchase pickleball-related sports products through the platform. | Phạm Lê Tấn Huy | To Do | iter2 | none
14 | Cancel Booking | Field | User | Users can cancel a previously booked court. | Trần Minh Trung | To Do | iter2 | none
15 | Cancel Order | Product | User | Users can cancel their orders before they are processed. | Phạm Lê Tấn Huy | To Do | iter2 | none
16 | Payment with VNPAY | Payment | User | Users can complete their purchases or court bookings using the VNPAY payment gateway. | Trần Minh Trung,Phạm Lê Tấn Huy | To Do | iter2 | none
17 | View Field Pickleball | Field | User, Admin, Guest | Displays detailed information about available pickleball courts, including location, pricing, and booking status. | Trần Minh Trung | To Do | iter2 | none
18 | View Product Pickleball | Product | User, Admin, Guest | Displays details of available pickleball products, including descriptions, prices, and reviews. | Phạm Lê Tấn Huy | To Do | iter2 | none
19 | View Chart | Manager | Admin | Displays graphical reports on bookings, sales, and user activity for business insights. | Nguyễn Bùi Quốc Việt | Done | iter1 | none
20 | View User Account | Manager | Admin | Admins can see a list of registered users and their details. | Nguyễn Bùi Quốc Việt | Done | iter1 | none
21 | Ban User Account | Manager | Admin | Admins can restrict a user's access due to violations. | Nguyễn Bùi Quốc Việt | Done | iter1 | none
22 | Update User Account | Manager | Admin | Admins can modify user details if necessary. | Nguyễn Bùi Quốc Việt | Done | iter1 | none
23 | Delete User Account | Manager | Admin | Admins can remove a user from the platform. | Nguyễn Bùi Quốc Việt | Done | iter1 | none
24 | Create Product Sport | Manager | Admin | Admins can add new sports products to the system. | Phạm Lê Tấn Huy | To Do | iter3 | none
25 | Update Product Sport | Manager | Admin | Admins can edit product details such as price, stock, and description. | Phạm Lê Tấn Huy | To Do | iter3 | none
26 | Delete Product Sport | Manager | Admin | Admins can remove a product from the store. | Phạm Lê Tấn Huy | To Do | iter3 | none
27 | Update Field | Manager | Admin | Admins can modify field details, such as availability and pricing. | Nguyễn Bùi Quốc Việt | To Do | iter2 | none
28 | Delete Field | Manager | Admin | Admins can remove a field from the system. | Nguyễn Bùi Quốc Việt | To Do | iter2 | none
29 | Create Field | Manager | Admin | Admins can add new pickleball courts to the system. | Nguyễn Bùi Quốc Việt | To Do | iter3 | none
30 | View Booking History | Manager | Admin,User | Users and Admin can check their past and upcoming court reservations. | Nguyễn Bùi Quốc Việt | To Do | iter3 | none
31 | Update Booking | Manager | Admin | Allows users to modify an existing booking, such as changing the time or date. | Nguyễn Bùi Quốc Việt | To Do | iter3 | none
32 | Cancel booking | Manager | Admin | Admins can cancel Users's booking | Nguyễn Bùi Quốc Việt | To Do | iter3 | none
33 | View Order List | Manager | Admin | Admins can view users's order past and ongoing product orders. | Nguyễn Châu Quảng | To Do | iter4 | none
34 | Create Order | Manager | Admin | Admins can place an order for pickleball products. | Nguyễn Châu Quảng | To Do | iter4 | none
35 | Approve Order | Manager | Admin | Admins can review and approve pending orders before processing. | Nguyễn Châu Quảng | To Do | iter4 | none
36 | Update Order | Manager | Admin | Admins can modify order details, such as delivery status. | Nguyễn Châu Quảng | To Do | iter4 | none
37 | Cancel Order | Manager | Admin | Admins can cancel user's orders before they are processed. | Nguyễn Châu Quảng | To Do | iter4 | none

## Iter1
Iteration Tracking - Iteration 1
Information in the columns A-F must be provided as the planned scope for the iteration
Columns B-D are copied from the sheet Product
Columns E-J are updated/filled by the end of the iteration
# | Screen / Function | Feature | Screen/Function Description | In Charge | Status | SRS | SDS | Notes
HomePage | Landing | Admin, User, Guest | Displays an overview of the platform, including featured pickleball courts, sports products, and user options. | Trần Minh Trung | Done | II.3 | III.5
User Login | Auth | Admin, User | This is a pop-up screen which allows the user to enter email & password to login; on this page, there are also links for user to register new information or reset the password for the case s/he forget it | Trần Minh Trung | Done | II.1 | III.4
Register | Auth | User,Guest | Enables new users to create an account on the platform. | Trần Minh Trung | Done
Register with Google | Auth | User,Guest | Allows users to sign up quickly using their Google account. | Trần Minh Trung | Done
User Login with Google | Auth | User,Guest | Enables users to log in using their Google credentials. | Trần Minh Trung | Done
Search Product | Product | User, Admin, Guest | Enables users to search for sports products related to pickleball. | Phạm Lê Tấn Huy | Done
View Chart | Manager | Admin | Displays graphical reports on bookings, sales, and user activity for business insights. | Nguyễn Bùi Quốc Việt | Done
View User Account | Manager | Admin | Admins can see a list of registered users and their details. | Nguyễn Bùi Quốc Việt | Done
Ban User Account | Manager | Admin | Admins can restrict a user's access due to violations. | Nguyễn Bùi Quốc Việt | Done
Update User Account | Manager | Admin | Admins can modify user details if necessary. | Nguyễn Bùi Quốc Việt | Done
Delete User Account | Manager | Admin | Admins can remove a user from the platform. | Nguyễn Bùi Quốc Việt | Done
Note on G5: KienNT: The name of section in the SRS (software requirement specification) document
Note on H5: KienNT: The name of section in the SDS (software design specification) document

## Iter2
Iteration Tracking - Iteration 2
Information in the columns A-F must be provided as the planned scope for the iteration
Columns B-D are copied from the sheet Product
Columns E-J are updated/filled by the end of the iteration
# | Screen / Function | Feature | Screen/Function Description | In Charge | Status | SRS | SDS | Notes
Forget Password | Auth | User,Guest | Provides an option to recover a forgotten password via email verification. | Trần Minh Trung | Done
Chagne Password | Auth | User | Allows users to update their password for security purposes. | Trần Minh Trung | Done
Search Field | Field | User, Admin, Guest | Users can search for available pickleball courts based on location, time, and availability. | Trần Minh Trung | Done
Buy Product Sport | Product | User | Users can purchase pickleball-related sports products through the platform. | Phạm Lê Tấn Huy | To Do
Cancel Booking | Field | User | Users can cancel a previously booked court. | Trần Minh Trung | To Do
Cancel Order | Product | User | Users can cancel their orders before they are processed. | Phạm Lê Tấn Huy | To Do
Payment with VNPAY | Payment | User | Users can complete their purchases or court bookings using the VNPAY payment gateway. | Trần Minh Trung,Phạm Lê Tấn Huy | To Do
View Field Pickleball | Field | User, Admin, Guest | Displays detailed information about available pickleball courts, including location, pricing, and booking status. | Trần Minh Trung | To Do
View Product Pickleball | Product | User, Admin, Guest | Displays details of available pickleball products, including descriptions, prices, and reviews. | Phạm Lê Tấn Huy | To Do
Update Field | Manager | Admin | Admins can modify field details, such as availability and pricing. | Nguyễn Bùi Quốc Việt | To Do
Delete Field | Manager | Admin | Admins can remove a field from the system. | Nguyễn Bùi Quốc Việt | To Do
Note on G5: KienNT: The name of section in the SRS (software requirement specification) document
Note on H5: KienNT: The name of section in the SDS (software design specification) document

## Iter3
Iteration Tracking - Iteration 3
Information in the columns A-F must be provided as the planned scope for the iteration
Columns B-D are copied from the sheet Product
Columns E-J are updated/filled by the end of the iteration
# | Screen / Function | Feature | Screen/Function Description | In Charge | Status | SRS | SDS | Notes
View Profile | Auth | User | Allows users to view their personal information, booking history, and order history. | Trần Minh Trung | Done
Edit Profile | Auth | User | Users can update their personal details, contact information, and preferences. | Trần Minh Trung | Done
Book Field Pickleball | Field | User | Users can reserve a pickleball court for a specific date and time. | Trần Minh Trung | To Do
Create Product Sport | Manager | Admin | Admins can add new sports products to the system. | Phạm Lê Tấn Huy | To Do
Update Product Sport | Manager | Admin | Admins can edit product details such as price, stock, and description. | Phạm Lê Tấn Huy | To Do
Delete Product Sport | Manager | Admin | Admins can remove a product from the store. | Phạm Lê Tấn Huy | To Do
Create Field | Manager | Admin | Admins can add new pickleball courts to the system. | Nguyễn Bùi Quốc Việt | To Do
View Booking History | Manager | Admin,User | Users and Admin can check their past and upcoming court reservations. | Nguyễn Bùi Quốc Việt | To Do
Update Booking | Manager | Admin | Allows users to modify an existing booking, such as changing the time or date. | Nguyễn Bùi Quốc Việt | To Do
Cancel booking | Manager | Admin | Admins can cancel Users's booking | Nguyễn Bùi Quốc Việt | To Do
Note on G5: KienNT: The name of section in the SRS (software requirement specification) document
Note on H5: KienNT: The name of section in the SDS (software design specification) document

## Iter4
Iteration Tracking - Iteration 3
Information in the columns A-F must be provided as the planned scope for the iteration
Columns B-D are copied from the sheet Product
Columns E-J are updated/filled by the end of the iteration
# | Screen / Function | Feature | Screen/Function Description | In Charge | Status | SRS | SDS | Notes
View Order List | Manager | Admin | Admins can view users's order past and ongoing product orders. | Nguyễn Châu Quảng | To Do
Create Order | Manager | Admin | Admins can place an order for pickleball products. | Nguyễn Châu Quảng | To Do
Approve Order | Manager | Admin | Admins can review and approve pending orders before processing. | Nguyễn Châu Quảng | To Do
Update Order | Manager | Admin | Admins can modify order details, such as delivery status. | Nguyễn Châu Quảng | To Do
Cancel Order | Manager | Admin | Admins can cancel user's orders before they are processed. | Nguyễn Châu Quảng | To Do
Note on G5: KienNT: The name of section in the SRS (software requirement specification) document
Note on H5: KienNT: The name of section in the SDS (software design specification) document